## Tabelle1
Public Construction Snagging List
| Total Snags: 5 | Completed: 3 | Outstanding: 2
PROJECT NAME: Pine Street Public Restroom |  |  |  | DATE:
PROJECT NUMBER: |  |  |  | COMPLETED BY:
Snag # | Room/ area | Snag description |  | Trade | Date | Photo | Completed?
1 | Women's Restroom | No exit sign |  |  | 2023-12-15 |  | No
2 | Women's Restroom | Crack in stall 2's door |  |  | 2023-12-10 | Yes | No
3 | Women's Restroom | Broken tiles in stall 1 |  |  | 2023-12-10 | Yes | Yes
4 | Men's Restroom | Wrong faucet installed at one of the sinks |  |  | 2023-08-03 | Yes | Yes
5 | Men's Restroom | Missing towel dispensor |  |  | 2023-08-03 | Yes | Yes
6
7
8
9
10
11
12
13
14
15
16
17
Notes